## Main Sheet
Traffic Profile | Total number of TC | Planned Automation | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16
GPRS | 8 | 4 | WK1: 2; WK2: 2
EGPRS | 22 | 9 | WK3: 2; WK4: 2; WK5: 2; WK6: 3
ECGSM | 3
PEO | 2
Mixed(GPRS+EGPRS) | 10 | 2 | WK7: 2
Mixed(Legacy+ECGSM) | 2
Mixed(Legacy+PEO) | 1
Mixed(Legacy+ECGSM+PEO) | 6
Mixed(Legacy+DTM) | 3
Mixed(Legacy+DTM+PEO+ECGSM) | 3
Total | 60 | 15 | WK1: 2; WK2: 2; WK3: 2; WK4: 2; WK5: 2; WK6: 3; WK7: 2
Planned by end of week 07 | 15/64

## GPRS
S.No. | Test Team | Test Case ID | Test Case Description | Traffic Profile(GPRS,EGPRS,ECGSM) | Traffic(MS Classes and Coding scheme) | Feature Coverage | TC Identification | Current Status | Comments
1 | PCULT | PCULTASBSC19FP1_193305001 | PCUM functionality and stability with CS2,MSCLASS-5 MS on single AI core | GPRS | MS Class 5,CS 1 | GPRS,Single AI core
2 | PCULT | PCULTASBSC19FP1_193321001 | To verify that UL data transfer using full PCUM connectivity with CS1 coding scheme | GPRS | MS Class 1,CS1 | Max UL data TBF,GPRS
3 | PCULT | PCULTASBSC19FP1_193321002 | PCULTASBSC19FP1_193321002:To verify PCUM functionality and stability with CS-2 and MS CLASS-5. | GPRS | MS Class 5,CS2 | Multiplexing,GPRS
4 | PCULT | PCULTASBSC19FP1_193320001 | To verify long duration data transfer behaviour of PCUM in GPRS only static terriotory with EPS feature ON during PDP activation and de-activation. | GPRS | MS Class 5,CS2 | GPRS only with static territory PDP activation & de-activation with EPS feature. | Identified from mcBSCRel2
5 | PCULT | PCULTASBSC19FP1_193320002 | To verify long duration behaviour of PCUM with Admission control feature ON with continuos GPRS attach and detach procedure ongoing | GPRS | MS Class 1,CS1 | GPRS only with static territory ,attach & detach procedure verification. | Identified from mcBSCRel2
6 | PCULT | PCULTASBSC19FP1_193316001 | To verify maximum PCUM RTSL utilization when CS2 coding scheme is in use. | GPRS | CS2
7 | PCULT | PCULTASBSC19FP1_193316002 | To verify maximum PCUM RTSL utilization when CS3 coding scheme is in use. | GPRS | CS3
8 | PCULT | PCULTASBSC19FP1_193316003 | To verify maximum PCUM RTSL utilization when CS4 coding scheme is in use. | GPRS | CS4

## EGPRS
S.No. | Test Team | Test Case ID | Test Case Description | Traffic Profile(GPRS,EGPRS,ECGSM) | Traffic(MS Classes and Coding scheme) | Feature Coverage | TC Identification | Current Status | Comments
| PCULT | PCULTASBSC19FP1_193305002 | PCUM functionality and stability with MCS5,MSCLASS-5 MS on single AI core | EGPRS | MS Class 5,MCS 5 | EGPRS,Single AI core
| PCULT | PCULTASBSC19FP1_193321003 | To verify UL data transfer using full PCUM connectivity with MCS-5 coding scheme. | EGPRS | MS Class 1,MCS 5 | Max UL data TBF,EGPRS
| PCULT | PCULTASBSC19FP1_193321004 | To verify UL and DL data transfer using full PCUM connectivity with MCS-5 coding scheme. | EGPRS | MS Class 1,MCS 5 | Max UL/DL data TBF,EGPRS
| PCULT | PCULTASBSC19FP1_193321005 | To verify PCUM functionality and stability with MCS-5 MSCLASS-5. | EGPRS | MS Class 5,MCS 5 | Multiplexing,EGPRS
| PCULT | PCULTASBSC19FP1_193320003 | To verify long duration data transfer ack mode with EGPRS only dynamic territory and MPGB,EPS feature is in ON state. | EGPRS | MCS5 | EGPRS in dynamic territory,MPGB,pcu pooling ,EPS feature. | Identified from mcBSCRel2
| PCULT | PCULTASBSC19FP1_193320004 | Stability run with territory upgrades and downgrades with frequency hopping enabled in PCUM unit. | EGPRS | MS Class 1,MCS 5 | territory upgrade, downgrade , frequency hopping enabled, ALA enabled, LA enabled.
| PCULT | PCULTASBSC19FP1_193320005 | Removing and adding PCUM to PCU pooling during Long duration data transfer with EGPRS MS. | EGPRS | MS Class 5,MCS9,MCS5 | MPGB,PCU pooling with only 2000 EGPRS MS with MCS-9 coding scheme. | Identified from mcBSCRel2 |  | original regresion TC had PCUM-A & PCUM-B with static &dynmaic NSEI'S-->Current TC modified by removing PCUM-A unit.
| PCULT | PCULTASBSC19FP1 193317001 | Full PCUM connectivity, EDA_HMC in use, MCS-7, Multislot class 32 and maximum GB throughput | EGPRS | MS Class 5,MS Class 32,MCS 7 | EDA HMC
| PCULT | PCULTASBSC19FP1 193317002 | Long term data transfer with Service Area Reallocation in Super Extended Cells moved to Extended Cells to Normal cells, with EGPRS Static Territory | EGPRS | MS Class 5,MCS 5 | Extended Cell,Super Extended Cell
| PCULT | PCULTASBSC19FP1 193317003 | Single PCUM, full PCUM connectivity, 2 static and 2 dynamic NSE configured. WRR in use. Long term data transfer. EGPRS dynamic territory with MCS-7 in use. Long term attach and detach of high number of MS. | EGPRS | MS Class 5,MCS 7 | WRR,Multipoint GB
| PCULT | PCULTASBSC19FP1 193317004 | Multiple PCUM in PSE, Long term GB interface creation and deletion for multiple NSEs. | EGPRS | MS Class 5,MCS 5 | PCU Pooling,Multi point GB
| PCULT | PCULTASBSC19FP1_193305003 | To verify all SE cores of PCUM boots up and process calls when SE CORE is crashed | EGPRS | MS Class 5,MCS 5 | PCU Restart Handling,Crash and Traffic restoration
| PCULT | PCULTASBSC19FP1_193316004 | Long term data transfer with territory upgrades\downgrades using BCF LOCK/UNLOCK, Multi Slot Class 12(DLDC) (DL only). MSCR 4. | EGPRS | MS Class 12,MCS 5 | DLDC,Terrritory upgrade/downgrade
| PCULT | PCULTASBSC19FP1_193316005 | To verify maximum PCUM RTSL utilization when MCS1 coding scheme is in use. | EGPRS | MCS1
| PCULT | PCULTASBSC19FP1_193316006 | To verify maximum PCUM RTSL utilization when MCS2 coding scheme is in use. | EGPRS | MCS2
| PCULT | PCULTASBSC19FP1_193316007 | To verify maximum PCUM RTSL utilization when MCS3 coding scheme is in use. | EGPRS | MCS3
| PCULT | PCULTASBSC19FP1_193316008 | To verify maximum PCUM RTSL utilization when MCS4 coding scheme is in use. | EGPRS | MCS4
| PCULT | PCULTASBSC19FP1_193316009 | To verify maximum PCUM RTSL utilization when MCS6 coding scheme is in use. | EGPRS | MCS6
| PCULT | PCULTASBSC19FP1_193316010 | To verify maximum PCUM RTSL utilization when MCS7 coding scheme is in use. | EGPRS | MCS7
| PCULT | PCULTASBSC19FP1_193316011 | To verify maximum PCUM RTSL utilization when MCS8 coding scheme is in use. | EGPRS | MCS8
| PCULT | PCULTASBSC19FP1_193316012 | To verify maximum PCUM RTSL utilization when MCS9 coding scheme is in use. | EGPRS | MCS9
| PCULT | PCULTASBSC19FP1_193321017 | Long duration IB-NACC cell change in EGPRS territory. | EGPRS

## ECGSM
S.No. | Test Team | Test Case ID | Test Case Description | Traffic Profile(GPRS,EGPRS,ECGSM) | Traffic(MS Classes and Coding scheme) | Feature Coverage | TC Identification | Current Status | Comments
| PCULT | PCULTASBSC19FP1_193321006 | Long Duration UL and DL data Transfer in EC-GSM. | ECGSM | CC1,CC2,CC3,CC4 | ECGSM
| PCULT | PCULTASBSC19FP1_193321007 | UL and DL TBF Establishment and Data transfer in EC-GSM IoT mode with ASBSC when Link Adaptation, Adaptive Initial MCS selection is enabled or disabled BTSs | ECGSM | CC1,CC2,CC3,CC4 | ECGSM,ECGSM Link Adaptation
| PCULT | PCULTASBSC19FP1_193321008 | DL TBF Establishment on CCCH and Data transfer in EC-GSM IoT mode with ASBSC when Link Adaptation ,Adaptive Initial MCS selection is enabled or disabled BTSs | ECGSM | CC1,CC2,CC3,CC4 | ECGSM,ECGSM Link Adaptation

## PEO
S.No. | Test Team | Test Case ID | Test Case Description | Traffic Profile(GPRS,EGPRS,ECGSM) | Traffic(MS Classes and Coding scheme) | Feature Coverage | TC Identification | Current Status | Comments
| PCULT | PCULTASBSC19FP1 193320006 | Long Duration data transfer with PCUM restart and PCUM switchover with PEO MS profile. | PEO |  | PCUM Restart,PCUM Switc over,PEO
| PCULT | PCULTASBSC19FP1 193320007 | DL TBF Establishment on CCCH with PCUM unit, verify paging procedures and dummy paging procedure for PEO enabled MS | PEO |  | PEO,Paging

## Mixed(GPRS+EGPRS)
S.No. | Test Team | Test Case ID | Test Case Description | Traffic Profile(GPRS,EGPRS,ECGSM) | Traffic(MS Classes and Coding scheme) | Feature Coverage | TC Identification | Current Status | Comments
| PCULT | PCULTASBSC19FP1_193320008 | To verify PCUM functionality and stability for 24 hours when both composite cells and normal cells are configured. | EGPRS,CMST | MS Class 5,MCS5 | EGPRS dynamic territoey with Composite cells & normal cells configured. | Identified from mcBSCRel2
| PCULT | PCULTASBSC19FP1_193320009 | To verify long duration data transfer with dymamic PCU pooling in dynamic mix territory with frequent deletion and addition of PCUM from pcu pooling. | GPRS,EGPRS | CS2,MCS5 | GPRS ,EGPRS in dynamic territory,Dynamic pcu pooling ,MPGB | Identified from mcBSCRel2
| PCULT | PCULTASBSC19FP1_193316013 | PCUM Switchover during data transfer with GPRS and EGPRS. | GPRS,EGPRS | MS Class 5,MCS 5,CS2,MCS5 | PCUM Restart,PCUM Switc over
| PCULT | PCULTASBSC19FP1_193316014 | Host BCXU Switchover (controlled switchover) done during data transfer with Mixed RNW, CS2 + MCS5 | GPRS,EGPRS | MS Class 5,MCS 5 | Host BCXU Switchover
| PCULT | PCULTASBSC19FP1_193316015 | Mixed RNW, Dynamic territory, Long term data transfer with PS call make break, Gateway BCXU switchover | GPRS,EGPRS | MS Class 5,MCS 5 | Gateway BCXU Switchover
| PCULT | PCULTASBSC19FP1_193316016 | Verify that PCUM can handle 25000 NCCR contexts. | GPRS,EGPRS | MS Class 1,CS1 | NCCR
| PCULT | PCULTASBSC19FP1_193321009 | Long duration UL+DL data transfer in mixed territory with PCUM in use and inter AI core reallocations. | GPRS,EGPRS | MS Class 5,MCS 9,CS2 | UL/DL data transfer,AI re allocation
| PCULT | PCULTASBSC19FP1_193317005 | Long term NCCR enabled cell changes (NACC being toggled) in Mixed RNW, CS2+MCS5 , dynamic territory. | GPRS,EGPRS | MS Class 5,MCS 5,CS2 | NCCR,NACC
| PCULT | PCULTASBSC19FP1_193305004 | MPGB FUNCTIONALITY IMPROVEMENT WITH NRR LOAD SHARING WITH STATIC AND DYNAMIC SGSN CONFIGURATION.
| PCULT | PCULTASBSC19FP1_193321016 | Long duration data transfer in Mix (GPRS/EGPRS/DLDC) territory, RF hopping enabled in few BTS, Continuous territory downgrade/upgrade.

## Mixed(Legacy+ECGSM)
S.No. | Test Team | Test Case ID | Test Case Description | Traffic Profile(GPRS,EGPRS,ECGSM) | Traffic(MS Classes and Coding scheme) | Feature Coverage | TC Identification | Current Status | Comments
| PCULT | PCULTASBSC19FP1 193320010 | Long duration data transfer with MOCN feature ON | GPRS,EGPRS,EC-GSM |  | MOCN |  |  | Rewirte for GPRS,EGPRS
| PCULT | PCULTASBSC19FP1 193320011 | Territory upgrade and downgrade in long duration data transfer with EGPRS MS and EC-EGPRS MS. | GPRS,EGPRS,EC-GSM
MPGB improvement

## Mixed(Legacy+PEO)
S.No. | Test Team | Test Case ID | Test Case Description | Traffic Profile(GPRS,EGPRS,ECGSM) | Traffic(MS Classes and Coding scheme) | Feature Coverage | TC Identification | Current Status | Comments
1 | PCULT | PCULTASBSC19FP1 193320012 | Long Duration data transfer with GPRS,EGPRS MS and PEO MS profiles. | GPRS,EGPRS,PEO

## Mixed(Legacy+ECGSM+PEO)
S.No. | Test Team | Test Case ID | Test Case Description | Traffic Profile(GPRS,EGPRS,ECGSM) | Traffic(MS Classes and Coding scheme) | Feature Coverage | TC Identification | Current Status | Comments
1 | PCULT | PCULTASBSC19FP1_193321010 | Long duration Data transfer with GPRS,EGPRS,PEO and EC-GSM using ASBSC when Link Adaptation ,Adaptive Initial MCS selection is enabled or disabled BTSs. | GPRS,EGPRS,ECGSM,PEO |  | Mixed Profile
2 | PCULT | PCULTASBSC19FP1_193321011 | BCXU switchover during Long duration Data transfer with mix traffic profile. | GPRS,EGPRS,ECGSM,PEO |  | Mixed Profile
3 | PCULT | PCULTASBSC19FP1_193321012 | PCUM switchover during Long duration Data transfer with mix traffic profile. | GPRS,EGPRS,ECGSM,PEO |  | Mixed Profile
4 | PCULT | PCULTASBSC19FP1_193321013 | PCUM restart during Long duration Data transfer with mix traffic profile. | GPRS,EGPRS,ECGSM,PEO |  | Mixed Profile
5 | PCULT | PCULTASBSC19FP1_193321014 | Long duration Data transfer with Addition and deletion of PCU and NSEI with mix traffic profile. | GPRS,EGPRS,ECGSM,PEO |  | Mixed Profile
6 | PCULT | PCULTASBSC19FP1_193321015 | RRMU switchover during Long duration Data transfer with mix traffic profile. | GPRS,EGPRS,ECGSM,PEO |  | Mixed Profile

## Mixed(Legacy+DTM)
S.No. | Test Team | Test Case ID | Test Case Description | Traffic Profile(GPRS,EGPRS,ECGSM) | Traffic(MS Classes and Coding scheme) | Feature Coverage | TC Identification | Current Status | Comments
| PCULT | PCULTASBSC19FP1 1933170006 | DTM traffic, Mixed RNW, dynamic territory. | GPRS,EGPRS,CS,DTM | MS Class 5,MCS 5,CS2 | DTM
| PCULT | PCULTASBSC19FP1_193320013 | To verify DTM functionality during Data transfer with GPRS CS1 coding scheme and MS class 1 | GPRS,DTM | MS Class 1,CS1 | DTM ,MPGB &GPRS only with MS class=1 & with 2560 MS with CS1 coding scheme | Identified from mcBSCRel2
| PCULT | PCULTASBSC19FP1_193320014 | Long Duration data transfer of either CS or PS calls while DTM feature enabled at simulator,BTS and BSC end. | GPRS,CS

## Mixed(Legacy+DTM+PEO+ECGSM)
S.No. | Test Team | Test Case ID | Test Case Description | Traffic Profile(GPRS,EGPRS,ECGSM) | Traffic(MS Classes and Coding scheme) | Feature Coverage | TC Identification | Current Status | Comments
1 | PCULT | PCULTASBSC19FP1_193305005 | Long duration Data transfer with CS,PS(GPRS and EGPRS),EC-GSM using mcBSC BOCA or BOCB harware variant when Link Adaptation Adaptive Initial MCS selection is enabled or disabled BTSs. | GPRS,EGPRS,CS,ECGSM |  | Mixed Profile
2 | PCULT | PCULTASBSC19FP1_193320015 | Long Duration data transfer with heterogeneous core network in mixed profile.
3 | PCULT | PCULTASBSC19FP1_183315001 | CS paging request to MS during TBF Reallocation in NMO-I with ASBSC | CS, PS